## project WBS monitor
project: | Time Registration Application |  |  | remark | WBS id is reference to chapter in functional design (FD)
calculator: |  |  |  | remark | for FD: chapter are not chronological
date: | 2016-09-07 |  |  | do not | change the WBS id number for a task
WBS id | predecessor | task | requirement level (MoSCoW) | developer | Risc | duration, hr (plan) | duration, hr (do)
1 |  | Template zoeken |  | Rob
2 |  | Layout |  | Rob
3 |  | Database |  | Rob
4 |  | Login |  | Mohamed
5 |  | Homepage maken (nog niet ingelogd) |  | Rob
6 |  | Homepage maken (als er is ingelogd) |  | Rob
7 |  | Profielpagina |  | Mohamed
8 |  | Topics posten en ophalen |  | Mohamed& Rob
9 |  | Laatste post user /Aantal topics/Laatste post tijd |  | Rob
10 |  | Adminrechten voor bepaalde colleges |  | Mohamed
11 |  | Adminrechten voor gehele site |  | Mohamed
12 |  | CSS/HTML allemaal op orde maken |  | Rob
13 |  | PDF poster genereren op basis van post. |  | Mohamed
|  | total |  |  |  | 0 | 0
Als de bovenstaande taken goed functioneren, is de maker van de site klaar met de opdracht.
Handtekening opdrachtgever
Handtekening docent

## MoSCoW
M | MUST | Describes a requirement that must be satisfied in the final solution for the solution to be considered a success.
S | SHOULD | Represents a high-priority item that should be included in the solution if it is possible. This is often a critical requirement but one which can be satisfied in other ways if strictly necessary.
C | COULD | Describes a requirement which is considered desirable but not necessary. This will be included if time and resources permit.
W | WON'T | Represents a requirement that stakeholders have agreed will not be implemented in a given release, but may be considered for the future. (note: occasionally the word "Would" is substituted for "Won't" to give a clearer understanding of this choice).

## version
datum | door | versieomschrijving
2015-10-09 | kadi | originele basisversie aangepast aan ideeën van Six Sigma